## Sheet1
Project LetsRise NOW! - Yelp Clone
Feature | Completed | Date Started | Expected Completion Time (days) | Date Completed
Get the Front end templates ready |  | 17/9/2019 | 1 | 17/9/2019
Database Design |  | 17/9/2019 | 1 | 17/9/2019
Finalize Dashboard Design |  | 17/9/2019 | 1 | 17/9/2019
Display featured ads |  | 17/9/2019 | 1 | 17/9/2019
Update View for each ad and link to the featured ads |  | 17/9/2019 | 1 | 17/9/2019
Finalize the categories to use |  | 17/9/2019 | 1 | 17/9/2019
Update Testimonials |  | 17/9/2019 | 1 | 17/9/2019
Create blog model |  | 19/09/2019 | 1 | 19/09/2019
Display featured blog posts on the home page |  | 19/09/2019 | 1 | 19/09/2019
Display all blog posts on the blog page |  | 19/09/2019 | 1 | 19/09/2019
Link urls to the blog posts |  | 19/09/2019 | 1 | 19/09/2019
Login/Logout |  | 19/09/2019 | 1 | 19/09/2019
Sign Up |  | 19/09/2019 | 1 | 19/09/2019
List all ads on the ads page |  | 20/09/2019 | 1 | 20/09/2019
Pagination on ads list |  | 20/09/2019 | 1 | 20/09/2019
Filters for ads
Search bar | Search completed for search bar. Have to work on city and category | 20/09/2019
Update search results page |  | 20/09/2019 | 1 | 20/09/2019
OAuth2 Login |  | 21/9/2019 | 1 | 21/9/2019
Complete the page for single ads |  | 21/9/2019 | 1 | 21/9/2019
Decide on the image to use for ads |  | 21/9/2019 | 1 | 21/9/2019
Comments on Ads |  | 22/9/2019 | 1 | 22/9/2019
CRUD on blogs
Comments on blog posts
View posts by category page |  | 21/9/2019 | 1 | 21/9/2019
CRUD on Ads |  | 21/9/2019 | 1 | 21/9/2019
Rating |  | 21/9/2019 | 1 | 21/9/2019
Rest API
Trending Search
One User One ad - Pay for more
TinyMice on ad and blog posts
About
Contact us
Profile Page
Like button