## Sheet1
Project LetsRise NOW! - Yelp Clone
Feature | Completed | Date Started | Expected Completion Time (days) | Date Completed
Get the Front end templates ready |  | 17/9/2019 | 1 | 17/9/2019
Database Design |  | 17/9/2019 | 1 | 17/9/2019
Finalize Dashboard Design |  | 17/9/2019 | 1 | 17/9/2019
Display featured ads |  | 17/9/2019 | 1 | 17/9/2019
Update View for each ad and link to the featured ads |  | 17/9/2019 | 1 | 17/9/2019
Finalize the categories to use |  | 17/9/2019 | 1 | 17/9/2019
Update Testimonials |  | 17/9/2019 | 1 | 17/9/2019
Create blog model |  | 19/09/2019 | 1 | 19/09/2019
Display featured blog posts on the home page |  | 19/09/2019 | 1 | 19/09/2019
Display all blog posts on the blog page |  | 19/09/2019 | 1 | 19/09/2019
Link urls to the blog posts |  | 19/09/2019 | 1 | 19/09/2019
Login/Logout |  | 19/09/2019 | 1 | 19/09/2019
Sign Up |  | 19/09/2019 | 1 | 19/09/2019
List all ads on the ads page |  | 20/09/2019 | 1 | 20/09/2019
Pagination on ads list |  | 20/09/2019 | 1 | 20/09/2019
Search bar | Search completed for search bar. Have to work on city and category | 20/09/2019
Update search results page |  | 20/09/2019 | 1 | 20/09/2019
OAuth2 Login |  | 21/9/2019 | 1 | 21/9/2019
Complete the page for single ads |  | 21/9/2019 | 1 | 21/9/2019
Decide on the image to use for ads |  | 21/9/2019 | 1 | 21/9/2019
Comments on Ads |  | 22/9/2019 | 1 | 22/9/2019
CRUD on blogs |  | 22/9/2019 | 1 | 22/9/2019
Comments on blog posts |  | 22/9/2019 | 1 | 22/9/2019
View posts by category page |  | 21/9/2019 | 1 | 21/9/2019
CRUD on Ads |  | 21/9/2019 | 1 | 21/9/2019
Rating |  | 21/9/2019 | 1 | 21/9/2019
TinyMice on ad and blog posts |  | 22/9/2019 | 1 | 22/9/2019
About |  | 22/9/2019 | 1 | 22/9/2019
Contact us |  | 22/9/2019 | 1 | 22/9/2019
Profile Page
Like button
Rest API
Trending Search
One User One ad - Pay for more

## Sheet2
Project LetsRise
Section | Start Date | Estimated time to complete (hrs)
Research on Yelp | 2019-09-12 | 1
Design the database model | 2019-09-12 | 0.5
Collect necessary frontend templates | 2019-09-12 | 0.5
Prepare the template according to the requirements | 2019-09-12 | 1
Header and Footer | 2019-09-13 | 0.5
Featured ads | 2019-09-13 | 0.5
Featured ads | 2019-09-13 | 1
Testimonials | 2019-09-13 | 0.5
About us | 2019-09-13 | 0.5
Contact Page | 2019-09-13 | 0.5
Blog page | 2019-09-14 | 2
Link blog page modules to other required pages | 2019-09-14 | 0.5
Login/Logout | 2019-09-14 | 1
SignUp | 2019-09-14 | 0.5
Ad Page | 2019-09-15 | 2
Pagination | 2019-09-15 | 1
Search | 2019-09-15 | 2
OAuth2 Login | 2019-09-16 | 1
Comments | 2019-09-16 | 2
CRUD | 2019-09-16 | 2
Ratings | 2019-09-17 | 1
TinyMCE HTML input for contents | 2019-09-17 | 1
Profile Page | 2019-09-18 | 2
Like Button | 2019-09-18 | 1
Trending Search | 2019-09-19 | 2
Rest API | 2019-09-20 | 2

## Sheet3
Project LetsRise
| Start Date | Duration
Research on Yelp | 2019-09-12 | 1
Design the database model | 2019-09-13 | 1
Work on the frontend | 2019-09-13 | 1
Prepare the template according to the requirements | 2019-09-13 | 1
Header and Footer | 2019-09-14 | 1
Featured ads | 2019-09-14 | 1
Categories | 2019-09-14 | 1
Testimonials | 2019-09-14 | 1
About us | 2019-09-14 | 1
Contact Page | 2019-09-14 | 1
Blog page | 2019-09-15 | 1
Link blog page modules to other required pages | 2019-09-15 | 1
Login/Logout | 2019-09-15 | 1
SignUp | 2019-09-15 | 1
Ad Page | 2019-09-16 | 1
Pagination | 2019-09-16 | 1
Search | 2019-09-16 | 1
OAuth2 Login | 2019-09-17 | 1
Comments | 2019-09-17 | 1
CRUD | 2019-09-17 | 3
Ratings | 2019-09-20 | 1
TinyMCE HTML input for contents | 2019-09-21 | 1
Profile Page | 2019-09-22 | 2
Like Button | 2019-09-24 | 2
Trending Search | 2019-09-26 | 2
Rest API | 2019-09-28 | 5
Error Handling | 2019-10-03 | 1
Testing | 2019-10-04 | 7